# 2026 CoC NOFO process timeline

## June 2026 HUD renewals

| Time range | Task | Actions needed to complete or other notes | Person Responsible | Status |
| --- | --- | --- | --- | --- |
| 6/3/26 | Submit to GMA for renewals |  | Lauren |  |
| 6/4/26 | Forward HUD release of Fy2024/2025 listserv message |  | Laura |  |
| ? | eSnaps opens | Complete Project Application (PA) in eSnaps | Mike, Erin, Lynn, Laura |  |
| 7/20/26 | Submit draft PA to Coordinator | By due date set for all projects | Mike, Erin, Lynn |  |
| 7/27/26 | Submit PA in eSnaps | Submit in eSnaps | Mike, Erin, Lynn, Laura |  |

## 2026 CoC NOFO process/timeline for the lead agency (TENTATIVE) 6-12-26

| Time range | Task | Actions needed to complete task or other notes | Person Responsible | Status |
| --- | --- | --- | --- | --- |
| Before | Identify lead for submitting A2A to GMA for NOFO and related applications |  | Supervisor |  |
| 6/1/26-6/12/26 | Read, disseminate, create timeline and process |  | CoC Coordinator |  |
|  | Submit 5 A2A to GMA | Notify project leads when submitted | Supervisor |  |
| 6/8/26 | Prepare CoC site for FY2026 NOFO | Update to 2026 NOFO | Coordinator/Comm Planner | done |
| 6/9/26 | Post FY2026 NOFO to CoC site | Post FY2026 NOFO | Coordinator/Comm Planner | done |
| 6/10/26 | FC recommendation 2026 Priorities Renewal/New | Recommendations | FC/Coordinator/Perform Eval |  |
| 6/12/26 | Create overview document and timeline |  | Coordinator |  |
| 6/15/26 | FY2026 NOFO overview meeting | 2026 NOFO overview/timeline | Coordinator |  |
| 6/17/26 – 7/24/26 | 2026 Priorities to HHH committee to approve | Vote to approve | Markus |  |
| 6/15/26 | Host community meeting |  | CoC Coordinator |  |
| tbd | Office hours as needed |  | CoC Coordinator |  |
| 6/15/26 | Send messaging out to applicants + post website on timing |  | CoC Coordinator |  |
| 6/19/26-6/26/26 | Letter of intent release for renewals (forms) |  | CoC Inbox |  |
| 6/22/26 -7/1/26 | New project pre-app released - new projects (DV) posted & due (forms |  | CoC Inbox |  |
| tbd | Connect with projects that are unlikely to be funded in any scenario – will they apply for SSO or TH? If not, what are other options (PBVs? Housing Support?) |  | CoC Coordinator |  |
| 7/1/26 | Funding Committee start score/ranking (2-3 scenarios) |  | FC/Coordinator/Perform Eval |  |
| 7/2/26-7/6/26 | Review New Project pre-applications |  | FC/Coordinator/Perform Eval |  |
| 7/8/26 | Funding Committee rank Renewal and New – recommendation |  | FC/Coordinator/Perform Eval |  |
| 7/16/26 | Ranking Rec’s to HHH committee and vote | Vote to approve | Markus |  |
| 7/22/26 | Appeals due to CoC |  |  |  |
| 7/20/26 | Review Renewal project applications |  | CoC Coordinator |  |
| 6/26/26 Kick off meeting with HC team | Create teams for SME’s at Hennepin – assign narrative questions with due dates: |  | Coordinator/Supervisor/Perform Evaluator |  |
| 7/1/26 – due 7/15/26 | Detailed Instructions – send everyone piece – follow up at 7/13 see how going |  | Coordinator/PE/Supervisor |  |
| 7/17/26 – 7/24/26 | Review SME narratives and refine – run by David/Danielle/Markus |  | Coordinator/Performance Evaluator/Supervisor |  |
| 8/7/26 | Review & finalize NOFO narratives |  | Coordinator/Performance Evaluator/Supervisor |  |
| 8/10/26 – 8/14/26 | Consolidated App to HHH committee and vote | Vote to approve submission | Markus |  |
| 8/10/26 | Final Priority List post on HC site |  | Coordinator/Communication |  |
| 8/19/26 | Consolidated App approved post on HC site |  | Coordinator/Communication |  |
| 8/24/26 | Submit Priority List and Collab Application in e-snaps |  | Coordinator |  |
| 8/26/26 | HUD set submission deadline |  |  |  |

## Lessons learned

- Limit word count for narrative responses